## Sheet1
				days	prio
1	Bitcrust-db
1..1		Spent-tree
1.1.2			Validation-sequential	2	dec	Scanning double spents without skiplist
1.1.3			Validation-skipping it1	4	jan	First implentation of skips
1.1.4			Height-dependent rules	..	>>	This includes coinbase 100-blocklimit and softforks
1.2		Validation
1.2.1			Amounts	3	jan
1.2.2			PoW	5	jan
1.3		Interface
1.3.1			read/search API	10-15	mar/apr	Simple uniform interface to browse through txs & blocks
			Custom indexing	..	>>	Plan first
			Orphan lookups			Currently orphans tx/blocks are not directly accebssable

1.4		Config
1.5		Core
			File recovery	10		Almost in, but needs tricky tests
			Log analysis	5	jan	Auto extract benches

2	Bitcrust-net
2.1		peer manager
2.1.1			initial dev	5-10	feb
2.2		messages
2.2.1			simple message parsing	5-10	feb/mar	Initially ver,inv and blocks-only

3	Bitcurst-node

4	Bitcrust-monitor
		GUI
			Curses MVC framework	10-15	>>	Should be a small wrapper such that also other clients can be monitored
		CMD
			JSON core-interface	10-15		Compatible with core; subset of commmands
			RPC wrapper	3

8	Integration tests
		Docker setup			mar/apr
		Bench setup			mar/apr

9	Website
		layour		extrn	feb/mar
		logo		extrn	feb/mar
		content		extrn	feb/mar	Features intro & blogs